## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to submit a single question-answer pair so that I can evaluate one AI response. | Must | None | Intern A | Done
Sprint 2 | Sprint 2 | US-05 | As a system, I want to retrieve relevant reference documents using a RAG pipeline so that responses are evaluated against trusted knowledge. | Must | US-01 | Intern A | Done
Sprint 2 | Sprint 2 | US-06 | As a system, I want to generate embeddings and store documents in a vector database for efficient retrieval. | Must | None | Intern A | Done
Sprint 2 | Sprint 2 | US-07 | As a system, I want a Relevance Judge Agent to determine whether the response answers the given question. | Must | US-05 | Intern A | Done
Sprint 2 | Sprint 2 | US-08 | As a system, I want an Accuracy Judge Agent to verify factual correctness using retrieved context. | Must | US-05 | Intern A | Done
Sprint 2 | Sprint 2 | US-09 | As a system, I want a Hallucination Detection Agent to identify unsupported or fabricated information. | Must | US-05 | Intern A | Done
Sprint 3 | Sprint 3 | US-02 | As a user, I want to upload a CSV file containing multiple question-answer pairs so that I can perform batch evaluations. | Must | US-01 | Intern A | Done
Sprint 3 | Sprint 3 | US-03 | As a user, I want the system to validate uploaded input files so that invalid data is rejected before processing. | Must | US-02 | Intern A | Done
Sprint 3 | Sprint 3 | US-04 | As a system, I want to preprocess and clean input data before evaluation so that downstream modules receive consistent input. | Must | US-02 | Intern A | Done
Sprint 3 | Sprint 3 | US-10 | As a system, I want a Completeness Judge Agent to determine whether all aspects of the question have been answered. | Must | US-05 | Intern A | Done
Sprint 3 | Sprint 3 | US-11 | As a system, I want a Verdict Agent to combine all judge outputs into a final evaluation result. | Must | US-07, US-08, US-09, US-10 | Intern A | Done
Sprint 3 | Sprint 3 | US-12 | As a user, I want to view individual scores for relevance, accuracy, hallucination, and completeness so that I understand evaluation results. | Must | US-11 | Intern A | Done
Sprint 3 | Sprint 3 | US-13 | As a user, I want detailed reasoning for every evaluation score so that I understand why the score was assigned. | Must | US-12 | Intern A | Done
Sprint 3 | Sprint 3 | US-14 | As a user, I want an overall quality score for each evaluated response so that I can compare responses easily. | Must | US-12 | Intern A | Done
Sprint 3 | Sprint 3 | US-16 | As a user, I want to monitor batch evaluation progress so that I know the current processing status. | Should | US-02 | Intern A | Done
Sprint 4 | Sprint 4 | US-17 | As a user, I want evaluation results to be stored for future analysis and reporting. | Should | US-11 | Intern A | Done
Sprint 4 | Sprint 4 | US-19 | As a user, I want an analytics dashboard displaying quality metrics and trends so that I can monitor AI model performance. | Should | US-17 | Intern A | Done
Sprint 4 | Sprint 4 | US-20 | As a user, I want charts showing average scores, hallucination rate, and processing statistics so that I can analyze evaluation outcomes visually. | Should | US-19 | Intern A | Done
Sprint 4 | Sprint 4 | US-18 | As a user, I want to export evaluation results for reporting purposes. | Should | US-17 | Intern A | Done (delivered as structured PDF export rather than CSV/Excel)
Sprint 4 | Sprint 4 | US-23 | As a developer, I want API documentation for all evaluation services so that integration with external applications is easier. | Could | US-11 | Intern A | Done
Sprint 4 | Sprint 4 | US-24 | As a project manager, I want evaluation performance reports so that I can monitor system efficiency over time. | Could | US-19 | Intern A | Done
Sprint 4 | Sprint 4 | US-22 | As an administrator, I want application logs and error reports so that system issues can be diagnosed efficiently. | Could | US-11 | Intern A | Partially Done (structured logging on agent/RAG failures; no central log dashboard yet)
Sprint 4 |  | US-15 | As a user, I want the system to process multiple evaluations in parallel for faster batch execution. | Should | US-11 | Intern A | To Do (sequential processing with API rate-limit pacing implemented instead; parallelism deferred)
|  | US-21 | As an administrator, I want role-based access control so that only authorized users can manage evaluation data. | Could | None | Intern A | To Do (out of internship scope)

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours)
US-01 | T1 | Scaffold FastAPI backend and React frontend project structure | 2026-06-20 | 2026-06-21 | Intern A | Development | Done | 6
US-01 | T2 | Build single question/response input form and submit flow | 2026-06-21 | 2026-06-23 | Intern A | Development | Done | 8
US-01 | T3 | Select and integrate an LLM backend for evaluation calls | 2026-06-23 | 2026-06-29 | Intern A | Integration | Done | 10
US-05 | T4 | Integrate ChromaDB and build document ingestion/chunking | 2026-07-10 | 2026-07-12 | Intern A | Development | Done | 8
US-06 | T5 | Implement embedding + similarity retrieval for RAG context | 2026-07-12 | 2026-07-13 | Intern A | Development | Done | 6
US-07 | T6 | Build Relevance Judge Agent with scoring prompt | 2026-07-13 | 2026-07-14 | Intern A | Development | Done | 5
US-08 | T7 | Build Accuracy Judge Agent with reference-grounded scoring | 2026-07-14 | 2026-07-15 | Intern A | Development | Done | 5
US-09 | T8 | Build Hallucination Detection Agent with claim flagging | 2026-07-15 | 2026-07-17 | Intern A | Development | Done | 6
US-07 | T9 | Validate all three agents against real TruthfulQA/SQuAD samples | 2026-07-18 | 2026-07-21 | Intern A | Testing | Done | 8
US-10 | T10 | Build Completeness Judge Agent identifying specific omissions | 2026-07-21 | 2026-07-22 | Intern A | Development | Done | 5
US-11 | T11 | Build Verdict Agent: weighted scoring + Pass/Needs Improvement/Fail label | 2026-07-22 | 2026-07-23 | Intern A | Development | Done | 6
US-12 | T12 | Build per-dimension results display (score cards, gauges, radar chart) | 2026-07-23 | 2026-07-25 | Intern A | Development | Done | 8
US-02 | T13 | Build CSV batch upload endpoint and background job processing | 2026-07-25 | 2026-07-27 | Intern A | Development | Done | 8
US-16 | T14 | Build batch progress polling and results table UI | 2026-07-27 | 2026-07-28 | Intern A | Development | Done | 6
US-17 | T15 | Design and implement persistent storage for evaluation history | 2026-08-01 | 2026-08-03 | Intern A | Backend Development | Done | 8
US-19 | T16 | Build dashboard aggregation endpoint (totals, averages, trends) | 2026-08-03 | 2026-08-05 | Intern A | Backend Development | Done | 8
US-20 | T17 | Build dashboard charts (pie/bar/line) and filters | 2026-08-05 | 2026-08-07 | Intern A | Development | Done | 8
US-18 | T18 | Build structured PDF report export | 2026-08-07 | 2026-08-09 | Intern A | Development | Done | 6
US-23 | T19 | Write end-to-end automated test suite (22 tests) | 2026-08-09 | 2026-08-12 | Intern A | Testing | Done | 10
US-11 | T20 | Build and run scoring consistency validation across repeated runs | 2026-08-12 | 2026-08-14 | Intern A | Testing | Done | 6
US-24 | T21 | Write technical documentation and formal project report | 2026-08-14 | 2026-08-16 | Intern A | Documentation | Done | 8

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 1 | Uncertainty over which LLM backend to standardize on for agent calls. | Evaluated Claude API, Ollama (local), Gemini, and Groq; selected based on reliability and free-tier availability.
Sprint 2 | Day 3 | RAG retrieval crashed the evaluation pipeline when ChromaDB's embedding model was briefly unavailable. | Wrapped RAG retrieval in its own error boundary so it degrades to empty context instead of failing the request.
Sprint 2 | Day 6 | Judge agent JSON responses occasionally failed to parse due to markdown code fences in the LLM output. | Added a JSON-cleaning step in the base agent to strip code fences before parsing.
Sprint 2 | Day 9 | Needed an objective way to confirm agents were scoring correctly, not just plausibly. | Built a 20-case benchmark from real TruthfulQA and SQuAD samples and validated all three agents against it.
Sprint 3 | Day 2 | Verdict Agent needed a single actionable label, not just a raw score, for the results screen to be usable. | Added a Pass / Needs Improvement / Fail categorical label with defined score thresholds.
Sprint 3 | Day 5 | Batch results table was missing required interface fields (full response, hallucination findings, reasoning), caught during review. | Added expandable rows to the batch table exposing full response, flagged claims, and consolidated reasoning per row.
Sprint 3 | Day 8 | Batch evaluation of many rows risked being perceived as frozen with no feedback. | Added a live progress bar backed by a pollable job-status endpoint.
Sprint 4 | Day 2 | Dashboard needed persisted history, but the system was previously stateless — no evaluation was ever saved. | Added a persistence layer so every single and batch evaluation is automatically stored.
Sprint 4 | Day 5 | External LLM API hit a 429 rate limit mid-pipeline, failing evaluations outright. | Added retry-with-exponential-backoff on 429 responses, plus pacing between sequential agent calls.
Sprint 4 | Day 7 | A previously working model was deprecated by its provider mid-project, breaking evaluations with a quota error. | Diagnosed via full error-body logging, then switched to a currently supported model.
Sprint 4 | Day 10 | End-to-end test suite revealed RAG failures were not isolated from the rest of the evaluation pipeline. | Fixed the orchestrator to treat RAG retrieval failure as non-fatal, consistent with the project's fallback design principle, then re-verified with the test suite.
Sprint 4 | Day 13 | Password hashing library raised a compatibility error against the latest installed dependency version. | Pinned the dependency to a known-compatible version and re-verified authentication end to end.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2026-07-10 | 2026-07-21 | Intern A | Validate agent scoring against real benchmark datasets as soon as an agent is built, not at the end of the sprint. | Assuming an LLM API key or model is stable for the whole sprint without a health check. | Building a fallback path for every external dependency before considering a feature done. | Added a /health endpoint and benchmark validation script early in the sprint workflow.
2 | Sprint 3 | 2026-07-22 | 2026-08-01 | Intern A | Cross-check the results UI against the full list of required interface fields before marking a feature done. | Treating a feature as complete once the happy-path UI renders, without checking every required field is present. | Using mentor review as a real gate, not a formality, since it caught a genuine gap in the batch results table. | Added an explicit field-by-field checklist pass before closing UI-related user stories.
3 | Sprint 4 | 2026-08-02 | 2026-08-16 | Intern A | Writing automated tests before assuming a workflow is reliable, especially around external API failure modes. | Manually spot-checking a few happy-path cases as the only form of verification before calling something tested. | Treating every LLM-dependent call as something that can fail, and designing a fallback for it up front. | Adopted a 22-test end-to-end suite covering error handling and invalid input as a standing part of Definition of Done.