## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Intern A | 2026-07-20 | Judge agent responses occasionally failed to parse as JSON due to markdown code-fence wrapping in the LLM output. | Sprint 2 | Intern A | Functional | Added a cleaning step to strip markdown code fences before JSON parsing in the base agent. | 2026-07-20 | Closed | Verified against repeated agent calls.
2 | Intern A | 2026-07-29 | Batch evaluation results table did not display AI Response, Hallucination Findings, or Consolidated Reasoning, though required by the interface spec. | Sprint 3 | Intern A | UI/UX | Added expandable rows to the batch results table exposing all three missing fields per row. | 2026-07-29 | Closed | Caught during mentor review; verified fields render correctly.
3 | Intern A | 2026-08-04 | A previously working LLM model was deprecated by its provider mid-project, causing all evaluations to fail with a quota/availability error. | Sprint 4 | Intern A | Integration | Diagnosed via full API error-body logging, then switched the evaluation pipeline to a currently supported model and provider. | 2026-08-04 | Closed | Confirmed working via live evaluation after switch.
4 | Intern A | 2026-08-05 | External LLM API returned HTTP 429 (rate limited) mid-pipeline, causing evaluations to fail outright instead of degrading gracefully. | Sprint 4 | Intern A | Functional | Added retry-with-exponential-backoff on 429 responses and pacing between sequential agent calls. | 2026-08-05 | Closed | Verified no failures across multiple consecutive evaluations.
5 | Intern A | 2026-08-06 | Backend connection status indicator showed a false 'unreachable' state on initial page load due to a timing race with server startup. | Sprint 4 | Intern A | UI/UX | Added retry-with-backoff to the initial health check and periodic background re-checks. | 2026-08-06 | Closed | Verified badge reflects true backend status after fix.
6 | Intern A | 2026-08-12 | End-to-end test suite revealed that a failure in RAG retrieval crashed the entire evaluation request instead of degrading gracefully. | Sprint 4 | Intern A | Functional | Wrapped RAG retrieval in its own error boundary; evaluation now proceeds with empty context on retrieval failure. | 2026-08-12 | Closed | Fixed and re-verified via the automated end-to-end test suite.
7 | Intern A | 2026-08-13 | Password hashing library (passlib) raised a compatibility error against the latest installed version of its bcrypt dependency. | Sprint 4 | Intern A | Environment/Dependency | Pinned bcrypt to a version confirmed compatible with the installed passlib release. | 2026-08-13 | Closed | Verified authentication (signup/login) works end to end after the fix.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others
Functional
UI/UX
Integration
Environment/Dependency